ACADEMY BEYOND THIS WORLD

THE HIDDEN SYSTEM

GAME GRAPHIC PRODUCTION PLAN

Full Production Roadmap + Needed Graphic Asset List

|  | Source Basis Prepared from the uploaded ABTW: The Hidden System - Game Bible / Graphic Production Edition, Version 1.0. This document converts the canon into a practical graphic production plan, milestone roadmap, asset register, and QA checklist. |
| --- | --- |

"Reality is not fixed. It responds to how it is seen."

Version 1.0 | Production Planning Draft

For: Graphic Artists, Illustrators, 3D Artists, UI Artists, Technical Artists, Producers

# Document Control

| Field | Value |
| --- | --- |
| Project | Academy Beyond This World: The Hidden System |
| Document | Game Graphic Production Plan and Needed Graphic Asset List |
| Version | 1.0 |
| Primary Use | Planning, task assignment, art direction alignment, asset tracking, external vendor briefing |
| Canon Source | ABTW: The Hidden System - Game Bible / Graphic Production Edition, Version 1.0 |
| Production Principle | Perception over power; cinematic restraint; 70% normal / 30% strange; no combat or spectacle visual language |

## Contents

1. Executive Production Summary

2. Creative Direction Lock

3. Production Pipeline and Phases

4. Team Structure and Responsibilities

5. Needed Graphic Asset List

6. Visual Prototype and Vertical Slice Plan

7. Character Production Plan

8. Environment Production Plan

9. UI, Notebook, Symbols, FX, and Lighting Plan

10. Cinematic and Marketing Graphics

11. Technical Delivery Requirements

12. Folder Structure and Naming

13. Milestones, Dependencies, and Risks

14. QA, Approval, and Regeneration Rules

15. Briefing Templates and Final Checklists

# 1  Executive Production Summary

A practical conversion of ABTW canon into an art-production roadmap.

The goal of this production plan is to turn ABTW: The Hidden System into a clear, executable graphic-production workflow for a restrained 3D narrative adventure. The visual system must communicate that the Academy is alive, perceptive, ancient, emotionally safe, and quietly strange.

The most important production decision is restraint. The game must not look like combat fantasy, horror, cyberpunk, or spectacle magic. The player should feel that reality is listening because they noticed something, not because the world is showing off visual effects.

|  | Core Visual Mandate ABTW succeeds when the player feels: reality itself is listening. It fails when the player feels: the world is showing off magic. |
| --- | --- |

## Primary Production Objective

Create all game-ready visual assets for the first ABTW game demo and eventual full game production.

Establish a repeatable pipeline for character, environment, UI, symbol, anomaly, lighting, cinematic, and marketing assets.

Protect the ABTW canon by using approval gates, regeneration rules, and visual QA checklists.

Deliver a first playable visual slice centered on Chapter 1: East Corridor / First Shadow Delay.

## Minimum Graphic Package for First Demo

| Demo Asset | Priority | Reason |
| --- | --- | --- |
| Astra playable model | P0 | Player identity and core perception animations. |
| East Corridor | P0 | First location; establishes the Academy visual language. |
| Normal / Glitch / Activation corridor states | P0 | Demonstrates reality response and core world-state system. |
| Shadow Delay anomaly | P0 | First tutorial anomaly and primary Chapter 1 visual mechanic. |
| Notebook UI | P0 | Core mechanic, decision interface, and narrative memory system. |
| Record / Wait decision UI | P0 | First meaningful player choice and visual consequence. |
| First symbol set | P0 | Foundation of the Academy language. |
| Lumi and Nela polished placeholders or final models | P1 | Required to communicate Trio system. |
| Trio Activation FX | P0 | Most important visual event in Chapter 1. |
| Opening and closing cinematic shots | P1 | Provides emotional framing for the vertical slice. |

# 2  Creative Direction Lock

Rules every artist must follow before producing final graphics.

## Art Direction in One Sentence

|  | Target Feel Studio Ghibli softness + Journey atmosphere + quiet mystery + living school environment. The Academy should feel 70% normal and 30% strange. |
| --- | --- |

## What the Game Must Feel Like

| Target Feeling | Graphic Method |
| --- | --- |
| Calm mystery | Soft lighting, restrained compositions, long pauses, quiet spatial depth. |
| Emotional safety | Warm gold, ivory, navy, soft shadows, inhabited spaces. |
| Curiosity | Small inconsistencies, subtle hidden details, repeated motifs. |
| Living Academy | Dressing, signs of student life, spaces that respond without spectacle. |
| Perception-based gameplay | Visual clues guide the eye instead of using forceful markers. |
| Subtle strangeness | Anomalies are wrong by a small amount; reality shifts quietly. |

## Forbidden Visual Direction

| Forbidden Direction | Production Warning Signs |
| --- | --- |
| Combat / power fantasy | Battle poses, impact frames, speed lines, attack animations, heroic running. |
| Spectacle magic | Fireballs, energy blasts, explosions, dramatic transformations, intense particle systems. |
| Horror / grimdark | Blood, body horror, threatening darkness, jump-scare framing, hostile shadows. |
| Cyberpunk / sci-fi drift | Neon UI, digital grids, futuristic panels, tech-like interfaces. |
| Theme-park fantasy | Overdesigned magical décor, whimsical excess, obvious magical displays. |
| Empty architecture showcase | Beautiful spaces with no life, no emotional function, no signs of use. |
| Game-level feeling | Obvious boundaries, checkpoint markers, artificial corridors, asset repetition without story. |

## Colour DNA

| Colour | Hex | Meaning | Usage |
| --- | --- | --- | --- |
| Deep Navy | #1A2942 | Mystery, perception, depth | Primary environment colour, night states, identity anchor |
| Indigo | #2D3A6B | Cognitive depth, understanding | Astra palette, symbols, secondary environment tone |
| Violet | #5B4A8A | Instability, hidden layers | Anomaly states, glitch moments, symbol forming |
| Warm Gold | #C9A84C | Reality anchor, belonging, activation | Trio Activation, notebook highlights, warm spaces |
| Muted Magenta | #8B4A6B | Awareness, perception shift | Perception UI, awareness indicators |
| Slate Blue | #4A5568 | Calm grounded reality | Normal state environments, character outlines |
| Ivory / Parchment | #F9F2E7 | Knowledge, memory, safety | Notebook pages, dormitory spaces, Archive lighting |
| Soft Cyan | #7EC8C8 | Analysis, clarity | Lumi, Clarity stat indicators, analytic notes |

## Rendering and Lighting Rules

Rendering style: painterly softness, stylised cinematic, not photoreal and not cartoon.

Character forms: rounded, readable, emotionally grounded, no harsh silhouettes.

Textures: hand-painted feel; avoid photographic grit or hyperreal materials.

Lighting: soft and diffused; no harsh directional light unless specifically approved for a story beat.

Anomaly lighting: subtle 10% temperature shift, not a dramatic colour replacement.

Bloom: very light and mostly limited to gold activation elements.

Post-processing: subtle colour grading; no lens flare or chromatic aberration as default treatment.

# 3  Production Pipeline and Phases

A phased workflow from canon lock to full graphic production.

| Phase | Name | Timing | Purpose | Main Deliverables |
| --- | --- | --- | --- | --- |
| 0 | Canon Lock & Visual Alignment | Week 1 | Confirm rules, palette, visual do/don't board, file structure, naming, state definitions. | Art Bible addendum, palette sheet, folder structure, approval checklist |
| 1 | Visual Prototype | Weeks 2-4 | Create one visual slice around East Corridor and the first Shadow Delay anomaly. | Astra prototype, East Corridor blockout, Notebook UI mock, anomaly shader test |
| 2 | Vertical Slice | Weeks 5-8 | Build Chapter 1 playable art target with normal/glitch/activation states and first Trio event. | Polished corridor, Record/Wait UI, Lumi/Nela placeholders, Trio Activation FX |
| 3 | Chapter 1 Production | Weeks 9-16 | Complete final models, animations, environments, symbol states, UI, and cinematic beats for Chapter 1. | Final Chapter 1 asset package, lighting LUTs, final integration checklist |
| 4 | Full Game Expansion | Weeks 17+ | Expand asset systems to Observatory, Archive, dorms, gardens, rooftops, hidden halls, supporting cast. | Location kits, full symbol library, marketing kit, production backlog updates |

## Asset Production Pipeline

Brief: Confirm canon, emotional target, state requirements, format, and priority.

Reference: Use only approved ABTW references and visual do/don't examples.

Concept: Produce silhouettes, colour tests, and state thumbnails before detail work.

Approval Gate 1: Art Director checks canon, tone, silhouette, palette, and forbidden drift.

Production: Build final 2D/3D asset, UI screen, shader, animation, or environment kit.

Technical Pass: Confirm engine compatibility, naming, optimization, material setup, and export formats.

Approval Gate 2: Creative Director confirms ABTW emotional correctness and visual restraint.

Integration: Import into engine, test scale, lighting, state changes, and gameplay readability.

QA: Run visual checklist, accessibility/contrast check, performance notes, and final signoff.

Archive: Save source, export, preview, and approval notes in the official folder structure.

## Priority Definitions

| Priority | Meaning | Examples |
| --- | --- | --- |
| P0 | Critical for first prototype or vertical slice. Cannot be delayed. | Astra, East Corridor, Shadow Delay, Notebook UI, Record/Wait UI, Trio Pulse. |
| P1 | Required for Chapter 1 completion or demo polish. | Lumi, Nela, Observatory first pass, Archive first pass, hidden layer reveal. |
| P2 | Required for full game production expansion. | Dormitories, gardens, classrooms, supporting cast, marketing posters. |
| P3 | Later expansion, optional polish, or non-demo features. | Full hidden halls set, art book pages, wallpaper sets, secondary variants. |

# 4  Team Structure and Responsibilities

Recommended roles for reliable graphic production.

| Role | Responsibilities | Key Outputs |
| --- | --- | --- |
| Creative Director | Owns canon, approves visual drift decisions, protects ABTW tone. | Canon approval; regeneration authority |
| Art Director | Maintains style guide, palette, render look, visual consistency across departments. | Daily visual reviews; style corrections |
| Producer / Art PM | Schedules milestones, tracks asset register, organizes approvals and dependencies. | Production board; risk log; handoff tracker |
| Concept Artist | Character, environment, prop, symbol, and anomaly concepts. | Approved concept packs; do/don't boards |
| Character Artist | 3D models, topology, textures, material pass, rig handoff readiness. | Game-ready characters; texture sets |
| Environment Artist | Architecture kits, dressing, materials, state variants, optimization support. | Modular location kits; set dressing packages |
| UI / UX Artist | Notebook, HUD, menus, icons, rank badges, prompts, accessibility-ready layouts. | UI kit; screens; icon library; button states |
| Technical Artist | Shaders, materials, state transitions, engine integration, performance budgets. | Shader library; integration notes; test scenes |
| VFX / Shader Artist | Anomaly FX, Trio Activation, echo states, symbol formation, subtle reveal effects. | FX prefabs; shader graphs; test captures |
| Lighting Artist | Time-of-day, location mood, cinematic lighting, LUTs, readability pass. | Lighting profiles; LUTs; screenshot QA |
| Animator | Idle, walk, notice, notebook, trio, companion motion, facial expression support. | Animation reference pack; final clips |
| QA / Visual Reviewer | Checks art against canon, readability, clipping, contrast, accessibility, performance. | QA reports; pass/fail sign-off |

## Review Cadence

| Meeting / Review | Frequency | Purpose | Owner |
| --- | --- | --- | --- |
| Canon Alignment Review | Once at project start; repeat before new chapter/location | Confirm that briefs and references match ABTW canon. | Creative Director |
| Daily Art Check | Daily during production | Catch visual drift early; review WIP snapshots. | Art Director |
| Technical Integration Review | 2x per week | Validate shaders, materials, scale, performance, naming, and engine handoff. | Technical Artist |
| Milestone Gate Review | End of every phase | Approve deliverables against milestone criteria and asset register. | Producer + Leads |
| Final Visual QA | Before asset lock | Use checklist and regeneration criteria to approve or reject assets. | QA + Art Director |

# 5  Needed Graphic Asset List

Complete asset register by production category.

## 5.1 Characters and Creature/Entity Assets

| Character | Priority | Role | Needed Graphics | Canon Notes |
| --- | --- | --- | --- | --- |
| Astra | P0 | Playable character | Concept, turnaround, expression sheet, hair clip, bracelet, hoodie material, 3D model, textures, rig handoff, idle/walk/notice/notebook poses, UI portrait, key art. | Dark indigo-purple hair; star hair clip left side; oversized cosmic hoodie; thoughtful non-aggressive posture. |
| Lumi | P1 | Analyst companion | Concept, turnaround, notebook prop, expression sheet, writing animation ref, 3D model, textures, UI portrait, Trio Activation pose. | Light blonde neat hair; white shirt; mint cardigan; navy trousers; precise notebook-centred silhouette. |
| Nela | P1 | Aligner companion | Concept, turnaround, earrings detail, dynamic pose sheet, movement ref, 3D model, textures, UI portrait, timing/activation pose. | Warm auburn curly hair; star/moon mismatched earrings; orange-gold jacket; dynamic asymmetric silhouette. |
| Prof. Lyra Quill | P2 | Mentor | Concept, 3D model, robe material, expression sheet, window/mentor poses, portrait. | Silver-streaked hair; layered robes; warm, measured, slightly melancholy. |
| Archivist Noctra | P2 | Lorekeeper | Concept, 3D model, silent movement reference, Archive lighting test, portrait. | Tall, dark clothing; quiet ancient presence; no visible carried items. |
| Orion Vex | P2 | Rival / foil | Concept, structured uniform, expression sheet, 3D model, posture and dialogue poses. | Sharp features; composed posture; competitive but secretly uncertain. |
| Mr. Vale / Curator | P2 | Order-driven administrator | Concept, 3D model, clipboard prop, formal pose sheet, expression variations. | Precise clothing; no visible anomaly reactions; slightly unsettling normalcy. |
| Nimbus | P1 | Emotional companion entity | Creature/entity design, colour-emotion states, float animation, glow shader, UI/icon variants. | Small luminous entity; shifts colour with emotional state; expressive but wordless. |

## 5.2 Environment Assets

| Location | Priority | Function | Needed Graphics | State / Tone Notes |
| --- | --- | --- | --- | --- |
| East Corridor | P0 | Chapter 1 tutorial / observation | Full concept, layout, blockout, modular kit, high vaulted ceiling, stone/wood materials, dark polished stone floor, windows, reflection shader, normal/glitch/activation lighting, Shadow Delay zone. | Warm gold normal state; cool shift in glitch; gold + violet activation; corridor must feel larger than characters. |
| Observatory | P1 | Wonder / cosmic awareness | Interior/exterior concept, ancient brass telescope, shifting star map ceiling, circular floor symbol, incomplete circle variants, night/activation lighting. | Cool navy and gold; quiet scale; cosmic but restrained. |
| Archive / Library | P1 | Hidden truth / investigation | Underground archive kit, shelves, narrow stacks, book variants, unknown scripts, changing-title textures, mirrors, amber lamps, deep blue light sections. | Warm reading light near player; cool hidden depth; intelligent and ancient. |
| Classrooms | P2 | Social warmth / routine | Classroom concept, desks, chairs, boards, educational props, student-life dressing, low-anomaly normal state. | Warm, grounded, inhabited, low anomaly frequency. |
| Dormitories | P2 | Safety / memory / vulnerability | Astra room, common room, beds, desks, personal objects, recovery lighting, night variant, memory trace locations. | Very low anomaly; safe space; soft emotional recovery atmosphere. |
| Gardens | P2 | Reflection / reset | Seasonal variants, plant modular kits, spiral plant anomaly, mist, rain, reflective puddle materials. | Nature mirrors emotion; seasonal changes support mechanics. |
| Rooftops | P2 | Perspective / revelation | Skyline views, sunset/night versions, high-anomaly activation state, symbol connection visuals. | High perspective, quiet revelation, not spectacle. |
| Hidden Halls | P3 | System beneath system | Hidden corridor concept, symbol-covered surfaces, golden thread system, reveal state, high anomaly version. | Deep mystery; high anomaly; still safe and restrained. |

## 5.3 Props and Hero Objects

| Prop | Priority | Function | Needed Graphics |
| --- | --- | --- | --- |
| Astra's Notebook | P0 | Core mechanic / UI object | Cover, leather material, paper pages, tabs, page-turn animation, glow/breathing states, Record/Wait state art. |
| Lumi's Notebook | P1 | Analysis object | Full prop design, overfilled pages, precise handwriting/diagrams, self-drawing activation animation. |
| Astra's Bracelet | P0 | Anomaly proximity cue | Subtle pulse material, close-up model, icon, shader pass; never flashy. |
| Astra's Star Hair Clip | P0 | Identity marker | Model detail, texture, close-up ref, silhouette visibility check. |
| Nela's Earrings | P1 | Identity marker | Star earring, moon earring, movement/jiggle reference, close-up sheet. |
| Observatory Telescope | P1 | Hero prop | Ancient brass model, lenses, interaction states, activation lighting response. |
| Archive Mirrors | P1 | Reflection anomaly surface | Mirror models, reflected-word material, distortion states, non-horror reflection rules. |
| Academy Doors | P1 | Reusable architecture prop | Door kit, handle variants, symbol placement zones, normal/hidden variants. |
| Window Frames | P1 | Lighting driver | Corridor frames, glass material, reflection tuning, warm light projection masks. |
| Books / Scrolls / Lamps | P2 | Archive and classroom dressing | Book variants, scrolls, lamp models, material library, lore texture variants. |
| Dormitory Objects | P2 | Emotional storytelling | Personal items, shelves, desk props, bedding, memory trace anchors. |
| Garden Plants | P2 | Seasonal system | Plant kit, seasonal materials, spiral anomaly model variants. |

## 5.4 UI / UX Graphics

| UI Category | Priority | Needed Graphics |
| --- | --- | --- |
| Notebook UI | P0 | Cover, page background, tabs, entries, page-turn animation, Record/Wait buttons, Deep Record, Echo entry state, glow/breathing state, auto-drawing state. |
| HUD | P0 | Perception ring, awareness, clarity, connection, timing, stability icons, anomaly indicator, interaction prompt, Observe/Record/Wait prompts, Trio Synchronization indicator. |
| Menus | P1 | Main menu, pause, settings, accessibility, chapter select, save/load, loading screen, controller/keyboard prompts, subtitle style. |
| Rank Badges | P2 | Observer, Noticer, Pattern Seeker, Interpreter, Aligner, System Aware, Influence Initiate, Reality Reader, System Shifter, Beyond Observer. |
| Dialogue / Portrait UI | P1 | Dialogue boxes, speaker labels, character portraits, low-distraction subtitle treatment, accessibility contrast states. |

## 5.5 Symbols

| Symbol | Priority | Required States | Use |
| --- | --- | --- | --- |
| Shadow Delay Symbol | P0 | Hidden, Glitch, Forming, Activation, Responding, Deepening, Consequence. | Used in East Corridor tutorial. |
| Incomplete Circle Symbol | P1 | Hidden, Glitch, Forming, Activation, Responding, Deepening, Consequence. | Used in Observatory; missing segment rotates between visits. |
| Reflected Word Symbol | P1 | Hidden, Glitch, Forming, Activation, Responding, Deepening, Consequence. | Used in Archive mirrors and reflective surfaces. |
| Corridor Echo Symbol | P1 | Hidden, Glitch, Forming, Activation, Responding, Deepening, Consequence. | Used in delayed footsteps/echo corridor system. |
| Trio Activation Symbol | P0 | Hidden, Glitch, Forming, Activation, Responding, Deepening, Consequence. | Central symbol for Chapter 1 activation event. |
| Echo Entry Symbol | P2 | Faded and incomplete variations of recorded-too-early patterns. | Supports consequence without punishment. |

## 5.6 Anomaly FX and Shader Assets

| FX / Shader | Priority | Needed Graphics / Technical Asset | Art Rule |
| --- | --- | --- | --- |
| Shadow Delay | P0 | Delayed shadow shader, cooler shadow tint, 0.3-0.5 sec offset, normal return state. | No harsh shadow jumps; must be readable but subtle. |
| Reflected Word | P1 | Reflection material showing alternate words in soft violet, mirror-specific distortion. | Avoid horror mirror language. |
| Incomplete Circle | P1 | Rotating missing segment, partial formation, activation glow, notebook recorded mark. | Geometric but hand-drawn; not digital. |
| Echo Corridor | P2 | Faint second footstep shadow, delayed rhythm, reduced-intensity echo visuals. | Approximately 40% intensity for echo states. |
| Memory Trace | P2 | Faint human outline visible only at night; soft dissolve; low-contrast state. | Suggestive, never ghost-horror. |
| Garden Spiral | P2 | Plant growth spiral pattern, seasonal expansion, subtle mathematical precision. | Natural first, strange second. |
| Hidden Layer Reveal | P1 | Soft reveal shader, new paths/symbols appearing with restrained gold/violet undertone. | Breath-like, not explosion. |
| Trio Pulse | P0 | Soft golden pulse from anomaly source, notebook glow, symbol completion. | Strongest FX in game, still quiet. |
| Golden Threads | P1 | Thin connection lines between related symbols/anomalies. | Readable only after connection; no neon. |

# 6  Visual Prototype and Vertical Slice Plan

The recommended first slice is Chapter 1: East Corridor / First Shadow Delay.

The vertical slice should not try to represent the entire game. It should prove the visual system: a living Academy, restrained anomalies, a physical notebook UI, and the first consequence choice. The slice should be small enough to finish and polished enough to define the full game.

## Vertical Slice Scope

| Component | Required Work | Acceptance Criteria |
| --- | --- | --- |
| Playable Astra | Final or near-final model, basic rig, idle/walk/notice/notebook interaction. | Player immediately reads Astra as thoughtful, observant, and non-combat. |
| East Corridor | Polished modular section with windows, vaulted scale, stone/wood materials, reflections. | Space feels larger than characters, inhabited, ancient, safe, and slightly aware. |
| Shadow Delay | Shader test implemented in scene with clear but subtle delay. | Players notice it through observation, not UI force. |
| Notebook UI | Physical notebook screen with tabs, Record/Wait buttons, entry states. | Feels like an object, not a digital menu. |
| Record / Wait Choice | Two visual consequence branches. | Record stabilises; Wait intensifies and allows Trio timing. |
| Trio Activation | Lumi/Nela presence, notebook self-drawing, soft gold pulse, hidden symbol reveal. | Moment feels important but not explosive. |
| Cinematic Framing | Opening corridor shot and closing reflective shot. | Communicates mystery and emotional warmth. |

## Vertical Slice Art Checklist

No combat interactions or combat-coded animation placeholders.

No generic magic VFX; all anomaly effects use subtle shader, distortion, delay, and controlled colour temperature shifts.

Notebook uses parchment, tabs, handwriting, and physical page transitions.

The corridor has signs of life and history: wear, maintenance, warmth, and scale.

First screenshot should communicate the full ABTW art direction without explanation.

# 7  Character Production Plan

Detailed steps for main trio, supporting characters, and identity assets.

## Character Production Steps

Canonical read: confirm character visual DNA, palette, pose restrictions, and silhouette requirements.

Exploration thumbnails: create 6-12 silhouettes without changing canon identity.

Concept sheet: front-facing design, material notes, accessory callouts, expression tone.

Turnaround: front, side, back, 3/4 if needed; include scale next to Astra baseline.

Expression sheet: emotionally readable but not exaggerated; avoid anime reaction extremes.

Pose sheet: idle, walk, notice, dialogue, notebook/trio interaction, neutral promotional pose.

3D model: final topology, rig-ready geometry, material IDs, texture maps.

Rig/animation handoff: joints, facial support, accessory secondary motion requirements.

UI portrait: dialogue and notebook portrait crops; readable at small sizes.

Promotional render: canon-accurate key pose for marketing and pitch materials.

## Main Trio Motion Rules

| Character | Motion Personality | Forbidden Motion |
| --- | --- | --- |
| Astra | Calm, observant, slightly slower than average; stops mid-step when noticing; head tilt and eye scanning. | Heroic sprint, power pose, combat stance, aggressive gestures. |
| Lumi | Precise, deliberate, upright, notebook-led; pen and page movement communicate analysis. | Frantic movement, slapstick, exaggerated anxiety. |
| Nela | Dynamic, asymmetric, slightly ahead of the moment; energetic without breaking tone. | Cartoon chaos, uncontrolled slapstick, combat acrobatics. |

## Character Approval Checklist

| Check | Question |
| --- | --- |
| □ | Can Astra, Lumi, and Nela be recognised in shadow alone? |
| □ | Does each character stay inside their assigned palette? |
| □ | Are accessories correct and visible enough: Astra star clip/bracelet, Lumi notebook, Nela star/moon earrings? |
| □ | Is posture emotionally grounded and non-aggressive? |
| □ | Are expressions readable without becoming exaggerated or comedic? |
| □ | Do promotional poses avoid battle/power/fantasy spectacle language? |

# 8  Environment Production Plan

The Academy as a living perception system, not a static fantasy school.

## Environment Production Steps

Emotional function definition: define what the space should make the player feel.

Layout and player flow: design for exploration, noticing, interpretation, choice, and reflection.

Blockout: establish scale first; corridors and key spaces must feel larger than characters.

Modular kit: walls, floors, doors, windows, ceiling pieces, trim, props, materials.

State system: normal, glitch, activation, hidden, echo variants where applicable.

Hero props: telescope, mirrors, notebook anchors, floor marks, windows, doors, symbols.

Lighting profile: time of day, colour temperature, anomaly shift, cinematic shot positions.

Set dressing: signs of life, age, maintenance, student presence, emotional realism.

Engine integration: colliders, material instances, lightmaps/LUTs, performance pass.

Screenshot polish: final composition views for review, marketing, and QA archive.

## Environment Emotional Function Matrix

| Location | Emotional Function | Pacing Role | Anomaly Frequency |
| --- | --- | --- | --- |
| East Corridor | Observation - the world is slightly wrong | Introduction / tension build | High, as tutorial space |
| Observatory | Wonder - scale and cosmic awareness | Breathing / reflection | Medium, symbolic |
| Archive / Library | Hidden truth - knowledge incomplete | Investigation / slow burn | Medium, layered |
| Classrooms | Social warmth - belonging and routine | Grounding / normalcy | Low, contrast |
| Dormitories | Vulnerability - safety and memory | Emotional recovery | Very low, safe space |
| Gardens | Reflection - nature as emotional mirror | Breathing / reset | Low, seasonal |
| Rooftops | Perspective - seeing the whole picture | Climactic / revelatory | High, activation |
| Hidden Halls | Deep mystery - system beneath system | Climax / discovery | Very high, hidden layer |

## East Corridor State Specification

| State | Visual Characteristics | Lighting Change | Production Assets |
| --- | --- | --- | --- |
| Normal | Calm, warm, stable; shadows behave; reflections mostly accurate but still slightly imperfect. | Warm gold dominant. | Base corridor kit, stable reflection shader, warm LUT, standard props. |
| Glitch | Shadows delayed 0.3-0.5 seconds; reflections show slight differences; light flickers once then stabilises. | Brief cool shift, then warm return. | Delayed shadow shader, cool-shift material state, wrong-reflection masks. |
| Activation | Symbols form on surfaces; light becomes directional and points toward pattern; reality feels responsive. | Gold intensifies with violet undertone. | Symbol formation, gold pulse, hidden layer reveal, directional lighting cue. |

# 9  UI, Notebook, Symbols, FX, and Lighting Plan

The non-character systems that make perception playable.

## Notebook UI Requirements

| Notebook Element | Required Graphic Treatment |
| --- | --- |
| Cover | Worn leather, dark navy-indigo, slightly too thick for binding. |
| Pages | Cream/ivory textured paper; not pure white; warm and tactile. |
| Ink System | Blue-black for Lumi, violet for Astra, amber for Nela, faded ink for Echo entries. |
| Tabs | Patterns, Symbols, Connections, Memory; colour-coded with restrained palette. |
| Page Animation | Slight resistance; notebook feels physical and alive. |
| Record Button | Clear, grounded, stabilising visual language. |
| Wait Button | Quiet tension; suggests patience and hidden depth. |
| Deep Record State | Gold glow, full symbol capture, no explosive FX. |
| Echo Entry | Faded, slightly blurred, incomplete mark; reads as trace, not failure. |
| Trio Auto-Drawing | Pages move and symbols appear on their own with precise, quiet animation. |

## Symbol State Production Rules

| State | Visual Requirement | Interaction Meaning |
| --- | --- | --- |
| Hidden | Invisible or absent; no visible asset until Awareness unlock. | Player cannot interact yet. |
| Glitch | Barely visible shimmer, wrong shadow, or reflection discrepancy. | Player notices through Awareness. |
| Forming | Incomplete lines fading in and out. | Player begins to interpret through Clarity. |
| Activation | Full symbol softly glowing in gold. | Trio presence becomes relevant. |
| Responding | Subtle pulse; environment reacts around it. | Player observes system response. |
| Deepening | Symbol connects to others via thin golden threads. | Player links related patterns. |
| Consequence | Permanent notebook mark; world state changed. | Player records and locks consequence. |

## Lighting Profiles

| Profile | Visual Mood | Anomaly Behaviour | Emotional Tone |
| --- | --- | --- | --- |
| Morning | Soft gold, mist, long shadows | Low frequency, subtle | Quiet awareness and fresh start. |
| Afternoon | Warm social light, busy corridors | Medium frequency, social | Belonging, routine, grounded warmth. |
| Sunset | Deep orange-gold, long dramatic shadows | High frequency, transitional | Emotional shift and anticipation. |
| Night | Deep navy, silver moonlight, stars visible indoors | Very high, perception depth | Silence, mystery, depth. |
| Rain | Grey-blue, reflective surfaces | Unstable, unpredictable | Reflection, instability, quiet unease. |
| Normal Corridor | Warm gold dominant | Stable | Calm tutorial state. |
| Glitch Corridor | Brief cool shift, then stabilise | Active | Something is slightly wrong. |
| Activation Corridor | Gold intensifies with violet undertone | High | Reality is responding. |
| Archive Surface | Amber reading lamps | Medium | Knowledge, focus, warmth. |
| Deep Archive | Cooler blue | Medium-high | Depth, uncertainty, hidden knowledge. |
| Observatory | Navy and gold cosmic light | Medium | Quiet wonder and scale. |

## Trio Activation Visual Sequence

Environment subtly dims; it becomes focused, not dark.

Lumi's notebook begins drawing on its own; pages turn and symbols appear.

Nela says, "Wait... now." This is the alignment cue.

A soft golden pulse radiates from the anomaly location.

The hidden layer appears: new symbols, new paths, new understanding.

UI shows TRIO SYNCHRONIZATION with subtle +Connection and +Awareness indicators.

|  | Trio FX Prohibition No explosions, no bright flashes, no combat-style effects, and no dramatic battle-music visual rhythm. The pulse should feel like a breath. |
| --- | --- |

# 10  Cinematic and Marketing Graphics

Dedicated visual moments and external-facing graphic assets.

## Chapter 1 Key Visual Moments

| Moment | Asset Type | Priority | Narrative / Production Function |
| --- | --- | --- | --- |
| Astra enters the East Corridor | Cinematic environment shot | P0 | First impression of Academy scale and emotional safety. |
| First Shadow Delay | Anomaly FX / tutorial shot | P0 | Player learns to notice, not fight. |
| Notebook opens for first time | UI animation | P0 | Core mechanic introduction; object must feel physical. |
| Record decision | Environment stabilisation FX | P1 | World calms, entry completes, consequence is visible. |
| Wait decision | Anomaly intensification FX | P1 | Pattern evolves; deeper layer becomes possible. |
| Lumi's notebook draws itself | Character animation / close-up | P1 | Trio system begins without spectacle. |
| Nela says "Wait... now" | Character performance beat | P1 | Timing and alignment moment. |
| Trio Activation | Environment + character FX | P0 | Most important visual event; soft gold pulse. |
| Hidden layer appears | Symbol/environment reveal | P1 | Reward for perception and patience. |
| Echo anomaly appears | Reduced-intensity FX | P2 | Consequence without punishment. |
| Astra looks back at corridor | Emotional closing shot | P1 | Quiet reflective end to Chapter 1. |

## Marketing and Promotional Asset Package

| Asset | Priority | Required Treatment | Use |
| --- | --- | --- | --- |
| Main Key Art | P1 | Astra, Academy corridor, subtle anomaly, Trio presence optional. | Storefront / pitch / press |
| Steam Capsule Set | P1 | Header, capsule, library hero, logo-safe versions. | PC launch preparation |
| Character Posters | P2 | Astra, Lumi, Nela, Nimbus; canon-accurate poses only. | Social, pitch, press kit |
| Trio Poster | P2 | Combined perception/analysis/alignment composition. | Brand identity |
| Academy Environment Poster | P2 | East Corridor or Observatory; no spectacle fantasy. | World showcase |
| Logo Treatment | P1 | Readable, restrained, compatible with navy/gold palette. | All channels |
| Title Screen Art | P1 | Quiet corridor, notebook, subtle symbol trace. | Game front end |
| Press Kit Screenshots | P1 | Curated Chapter 1 visual beats, no spoilers. | PR and publisher review |
| Trailer Title Cards | P2 | Short lines, notebook texture, restrained motion. | Trailer package |
| Social Media Posts | P2 | Square and vertical variants; character/environment quote cards. | Community/marketing |

## Marketing Art Rules

Marketing must not exaggerate magic beyond the actual game language.

Key art should communicate perception, friendship, mystery, and the living Academy.

Astra, Lumi, and Nela must remain canon-accurate; no outfit changes for marketing convenience.

Avoid generic fantasy school posters; the Academy is quieter and stranger.

All store capsules must remain readable at small sizes and must prioritize logo clarity.

# 11  Technical Delivery Requirements

Required formats, colour modes, file rules, and handoff expectations.

| Use | Format | Notes |
| --- | --- | --- |
| Source artwork | PSD / AI | Layered, named groups, editable source retained. |
| Game-ready 2D | PNG / WebP | sRGB; transparent where needed; export scale documented. |
| Print assets | TIFF / PDF | 300 DPI minimum; CMYK; 3mm bleed; safe margins. |
| UI icons | PNG with alpha | Multiple scale exports; readable at small sizes. |
| Textures | PNG / TGA / engine-preferred | Albedo, normal, roughness, masks where relevant. |
| Marketing | PNG / TIFF / PSD | Digital and print variants; logo-safe crops. |
| Technical FX | Shader graphs / materials / texture masks | Engine-ready, documented parameters, performance notes. |

## Print and Digital Requirements

Print materials: 300 DPI minimum, CMYK, 3mm bleed, KDP-safe margin of at least 0.375 inches.

Digital and game materials: RGB / sRGB unless engine requirements specify otherwise.

Source files: layered and non-destructive where possible; major layers and groups must be named.

Textures: include export resolution, material channel use, and engine import notes.

UI exports: include normal, hover/focus, selected, disabled, and accessibility/high-contrast variants where required.

Final packages: include source, export, preview image, integration note, and approval status.

## Engine Handoff Checklist

| Check | Requirement |
| --- | --- |
| □ | Asset name follows official naming convention. |
| □ | Scale is correct relative to Astra baseline. |
| □ | Pivot/origin is practical for placement or animation. |
| □ | Textures are exported in correct resolution and colour space. |
| □ | Materials have documented parameters and state variants. |
| □ | Animations include naming, frame rate, loop state, and transition notes. |
| □ | UI files include responsive/scale variants and interaction states. |
| □ | FX assets include performance notes and intensity limits. |
| □ | Preview screenshot or turntable is included. |
| □ | Art Director and Technical Artist have both signed off. |

# 12  Folder Structure and Naming

Recommended project organization for artists and engine integration.

## Folder Structure

ABTW_Assets/
  Characters/
    Astra/
    Lumi/
    Nela/
    Supporting/
  Environments/
    EastCorridor/
    Observatory/
    Archive/
    Classrooms/
    Dormitories/
    Gardens/
    Rooftops/
    HiddenHalls/
  Props/
    Notebook/
    Bracelet/
    Telescope/
    Mirrors/
    Books/
    Academy_Dressing/
  UI/
    Notebook/
    HUD/
    Menus/
    Icons/
    Rank_Badges/
  Symbols/
    Symbol_001_ShadowDelay/
    Symbol_002_IncompleteCircle/
    Symbol_003_ReflectedWord/
    Symbol_States_Template/
  FX/
    Anomalies/
    TrioActivation/
    Echo/
    HiddenLayer/
  Lighting/
    LUTs/
    TimeOfDay/
    EnvironmentProfiles/
  Cinematics/
    Chapter01/
    KeyMoments/
  Marketing/
    KeyArt/
    Posters/
    StoreAssets/
    SocialMedia/

## Naming Convention

| Asset Type | Naming Pattern | Example |
| --- | --- | --- |
| Character model | CHAR_[Name]_[Version] | CHAR_Astra_v001 |
| Character texture | TEX_CHAR_[Name]_[Material]_[Map]_[Res] | TEX_CHAR_Astra_Hoodie_ALB_2K |
| Environment module | ENV_[Location]_[Module]_[State]_[Version] | ENV_EastCorridor_Window_Normal_v003 |
| Prop | PROP_[Object]_[Variant]_[Version] | PROP_Notebook_Astra_v004 |
| UI screen | UI_[System]_[Screen]_[State]_[Version] | UI_Notebook_Patterns_Recorded_v002 |
| Icon | ICON_[System]_[Name]_[State] | ICON_Stats_Awareness_Normal |
| Symbol | SYM_[ID]_[Name]_[State]_[Version] | SYM_001_ShadowDelay_Forming_v001 |
| FX / Shader | FX_[Category]_[Name]_[Intensity]_[Version] | FX_Anomaly_ShadowDelay_Low_v002 |
| Lighting LUT | LUT_[Location]_[TimeOfDay]_[State] | LUT_EastCorridor_Afternoon_Glitch |

# 13  Milestones, Dependencies, and Risks

Production management overview for the graphic pipeline.

## Milestone Roadmap

| Milestone | Name | Deliverables | Exit Criteria |
| --- | --- | --- | --- |
| M0 | Production Setup | Canon packet, style guide, reference board, naming conventions, task board, approval cadence. | All departments can begin without visual ambiguity. |
| M1 | First Visual Target | East Corridor blockout, Astra prototype, first Notebook UI, Shadow Delay shader, palette test. | One screenshot proves the ABTW look. |
| M2 | Interactive Prototype | Player can walk, notice anomaly, open notebook, choose Record or Wait. | Core loop readable: Explore -> Notice -> Interpret -> Decide. |
| M3 | Vertical Slice | Final-quality corridor, trio moment, symbols, lighting states, UI, cinematic moments. | Publisher/demo-ready Chapter 1 sample. |
| M4 | Chapter 1 Content Complete | All Chapter 1 assets integrated and QA-approved. | End-to-end Chapter 1 art lock. |
| M5 | Full Production Expansion | Reusable environment kits, additional locations, complete UI set, supporting cast. | Production moves from demo into scalable content creation. |

## Key Dependencies

| Dependency | Needed Before | Why It Matters |
| --- | --- | --- |
| Canon visual packet | All art production | Prevents palette, silhouette, and style drift. |
| Astra baseline model | Environment scale, animations, UI portrait work | All scale and camera framing should use Astra as baseline. |
| East Corridor blockout | Shadow Delay, lighting, cinematic shots | The first location is the master visual target. |
| Notebook UI wireframe | UI art, narrative entries, Record/Wait implementation | Core mechanic must be designed early. |
| Symbol state template | All symbol production | Prevents inconsistent symbol language across chapters. |
| Anomaly shader prototype | FX library and environment states | Defines the technical look of wrongness. |
| Lighting LUTs | Environment polish and screenshot approval | Locks the ABTW emotional colour language. |

## Production Risks and Mitigation

| Risk | Severity | Impact | Mitigation |
| --- | --- | --- | --- |
| Anomaly FX becomes too flashy | High | Breaks the core visual contract; game feels like spectacle fantasy. | FX review gate; enforce shader-first subtlety; compare to 70/30 rule. |
| Academy environments feel empty | High | World loses emotional intelligence and living-school quality. | Set dressing checklist; social-life props; daily occupancy review. |
| Characters drift from canon | High | Brand identity and story consistency are damaged. | Turnaround lock; silhouette tests; no unapproved outfit changes. |
| Notebook UI feels digital | Medium | Core mechanic loses physical and emotional value. | Paper-first design; handwritten entries; avoid neon/digital widgets. |
| Tables/assets lack engine readiness | Medium | Integration delays and rework. | Technical art signoff before final asset approval. |
| Lighting becomes too dramatic | Medium | Visual tone shifts toward horror/fantasy spectacle. | Lighting mood boards; soft shadows; subtle colour shifts only. |
| Overbuilding Chapter 1 | Medium | Schedule risk and asset bloat. | Prioritize P0/P1; freeze nice-to-have marketing assets until slice lock. |

# 14  QA, Approval, and Regeneration Rules

How to protect the ABTW look during production.

## Per-Asset QA Checklist

| Status | QA Area | Question |
| --- | --- | --- |
| □ | Emotional atmosphere | Does the asset feel calm, curious, safe inside mystery, and appropriate for its location? |
| □ | Colour DNA | Does it use approved ABTW palette values and avoid unapproved colour drift? |
| □ | Character consistency | Are hair, accessories, silhouettes, outfits, and posture canonical? |
| □ | Anomaly subtlety | Is the anomaly noticeable only through observation, not visual force? |
| □ | Scale | Do corridors and major spaces feel larger than the characters? |
| □ | Lighting | Is lighting soft, cinematic, emotionally correct, and not horror-coded? |
| □ | Forbidden elements | No combat, power poses, explosions, horror, cyberpunk, theme-park fantasy, or game-level markers. |
| □ | Readability | Can the player/viewer understand the visual beat without explanatory text? |
| □ | Engine readiness | Is the asset named, optimized, organized, and delivered in correct format? |
| □ | Approval status | Has the asset passed Art Director and Creative Director review? |

## Regeneration Criteria

| Failure Condition | Action | Reason |
| --- | --- | --- |
| Character design mismatch | Regenerate | If canonical visual DNA is wrong, revision wastes time; rebuild from approved reference. |
| Wrong emotional atmosphere | Regenerate | Threatening, comedic, generic, or spectacular tone breaks ABTW identity. |
| Anomaly too obvious | Regenerate | If the anomaly reads as magic FX, the asset fails the 70/30 rule. |
| Palette drift | Regenerate or recolour from source | Unapproved hues damage brand consistency. |
| Forbidden visual element present | Regenerate | Combat, horror, cyberpunk, spectacle fantasy, or theme-park imagery are hard failures. |
| Composition ignores narrative function | Revise or regenerate | Every image must serve a beat: observation, reflection, reveal, recovery, or connection. |
| Environment feels like game level | Regenerate blockout | Obvious level boundaries and empty layouts break the living Academy. |

## Approval Gates

| Gate | Approver | Must Confirm |
| --- | --- | --- |
| Brief Lock | Producer + Art Director | Priority, output format, scope, canon notes, dependencies. |
| Concept Approval | Art Director | Silhouette, composition, palette, emotional function, no forbidden drift. |
| Canon Approval | Creative Director | Visual DNA, world rules, emotional tone, restraint. |
| Technical Approval | Technical Artist | Scale, topology, materials, shader behavior, file naming, engine import. |
| Final Art Lock | Art Director + QA | Checklist pass, no visible defects, preview archived. |

# 15  Briefing Templates and Final Checklists

Reusable production templates for the graphic team.

## Illustration / Asset Brief Template

| Field | What to Fill In |
| --- | --- |
| Page / Asset Type | Classic Split, Soft Hybrid, Cinematic Full, Notebook, Archive, Reflection, 3D asset, UI asset, FX asset. |
| Location | Specific Academy space: East Corridor, Observatory, Archive Level 2, dormitory hall, etc. |
| Time of Day | Morning, afternoon, sunset, night, rain. |
| Season | Autumn, winter, spring, summer, if applicable. |
| Characters Present | List characters and emotional state. |
| Anomaly State | None, Glitch, Forming, Activation, Responding, Deepening, Consequence, Echo. |
| Emotional Target | One sentence describing how the player/viewer should feel. |
| Narrative Function | What story beat or mechanic this asset supports. |
| Colour Temperature | Warm, cool, mixed; include notes on gold/navy/violet balance. |
| Forbidden Elements | Specific drift risks to avoid for this asset. |
| Technical Output | Required format, resolution, texture maps, engine prefab, or layered file requirements. |
| References | Approved ABTW references only; no unapproved fantasy/sci-fi drift. |

## Final Delivery Package Checklist

| Status | Deliverable |
| --- | --- |
| □ | Layered source file or editable 3D source file included. |
| □ | Game-ready export included in approved format. |
| □ | Preview image or turntable included. |
| □ | Asset metadata includes priority, owner, version, approval status, and notes. |
| □ | No forbidden visual direction present. |
| □ | Colour palette verified against ABTW World Colour DNA. |
| □ | Character or environment scale validated in scene. |
| □ | UI contrast/readability checked where applicable. |
| □ | Shader/FX intensity tested in normal gameplay camera, not just close-up. |
| □ | Final asset archived in official folder structure. |

## Final Production Summary

The first ABTW graphic production milestone should focus on a restrained but polished visual slice: Astra in the East Corridor, the first Shadow Delay anomaly, the physical Notebook UI, the Record/Wait decision, and the first Trio Activation. If these pieces feel correct, the rest of the game can scale from a stable visual foundation.

The success metric is not visual loudness. The success metric is whether the player becomes more observant. Every asset should make the player feel that the Academy is a living, emotionally intelligent system that responds to perception.

|  | Final Rule for Artists Do not show magic. Design the moment when the player notices that reality has changed. |
| --- | --- |