ACADEMY BEYOND THIS WORLD

THE HIDDEN SYSTEM

MASTER PRODUCTION SCHEDULE

Version 1.0 — Full Production Authority

Departments: Graphic Production & Programming

Timeline: 12 Months — Parallel Production

Phases: Pre-Production → Alpha → Beta → Gold

Team: Small Indie Studio (3–5 people)

"Every asset, every script, every system — rooted in the same canonical world."

— ABTW Production Principle

📗 Graphic Bible    +    📘 Programming Bible

Both bibles govern this schedule. All tasks reference their respective bible.

# Table of Contents

1. Production Overview & Principles

2. Department Structure & Roles

3. Phase 1 — Pre-Production (Months 1–2)

4. Phase 2 — Alpha (Months 3–6)

5. Phase 3 — Beta (Months 7–10)

6. Phase 4 — Gold / Launch (Months 11–12)

7. Inter-Department Dependencies

8. Task Priority Matrix

9. Milestone Summary

10. Canon Compliance Rules

# 1. Production Overview & Principles

## 1.1 Document Purpose

This Master Production Schedule governs all production activity for Academy Beyond This World: The Hidden System. It coordinates two parallel production departments — Graphic and Programming — ensuring that every asset, script, and system is delivered on time, in the correct order, and in full compliance with the canonical ABTW world rules.

This schedule is derived directly from the two Master Production Bibles:

📗 Graphic Production Bible: Visual & art direction guide for illustrators and graphic artists

📘 Programming Bible: Complete technical architecture guide for developers

"The schedule is not a constraint. It is the structure that allows the world to be built correctly."

## 1.2 Production Parameters

| Parameter | Value |
| --- | --- |
| Total Timeline | 12 months (parallel production) |
| Team Size | Small indie studio — 3 to 5 people |
| Production Model | Parallel: Graphic + Programming run simultaneously |
| Phase Structure | Pre-Production → Alpha → Beta → Gold |
| Primary Platform | PC (Windows) — Console future expansion |
| Game Engine | Unity (C# scripting) |
| Art Style | Stylized cinematic — painterly, soft light, emotionally intelligent |
| Canon Authority | ABTW Legendary Master World Bible v1.0 (Full Canon Lock) |

## 1.3 Core Production Principles

Every production decision must be evaluated against these five principles:

Canon First: No asset or script may contradict the Master World Bible. Canon compliance is non-negotiable.

Perception Over Spectacle: Visual and technical choices must serve the perception-driven design philosophy. Subtlety is always preferred over spectacle.

Department Synchronisation: Graphic and Programming departments must communicate at every phase boundary. No department works in isolation.

Milestone Integrity: Milestones are hard deadlines. Missing a milestone triggers a mandatory cross-department review before proceeding.

Iterative Quality: Each phase builds on the previous. Alpha is functional, Beta is polished, Gold is canon-locked.

## 1.4 Phase Overview

| Phase | Months | Goal | Output |
| --- | --- | --- | --- |
| Pre-Production | Months 1–2 | Foundation — all systems designed, all assets planned | Design docs, asset lists, prototype level |
| Alpha | Months 3–6 | Core build — all primary systems functional, key assets created | Playable Chapter 1 (East Corridor) |
| Beta | Months 7–10 | Full content — all assets complete, all systems integrated | Full game build, QA-ready |
| Gold / Launch | Months 11–12 | Polish, certification, release | Final EXE, store submission |

# 2. Department Structure & Roles

## 2.1 Graphic Department

The Graphic Department is responsible for all visual assets — characters, environments, UI, symbols, FX, and promotional materials. All work must conform to the Graphic Production Bible.

| Role | Responsibilities | Bible Reference |
| --- | --- | --- |
| Lead Artist / Art Director | Canon compliance, style consistency, final approval on all assets | Graphic Bible — Sections 6, 7 |
| Character Artist | Astra, Lumi, Nela, supporting characters — models, textures, expression sheets | Graphic Bible — Section 3 |
| Environment Artist | All Academy spaces — corridors, observatory, archive, dormitories, gardens | Graphic Bible — Section 4 |
| UI / UX Designer | Notebook UI, HUD, menus, perception ring, symbol displays | Graphic Bible — Section 5.3 |
| VFX Artist | Anomaly FX, Trio Activation pulse, symbol formation, shader effects | Graphic Bible — Sections 4.3, 5.4 |

## 2.2 Programming Department

The Programming Department is responsible for all C# scripts, Unity systems, data architecture, and build pipeline. All work must conform to the Programming Bible.

| Role | Responsibilities | Bible Reference |
| --- | --- | --- |
| Lead Developer / Technical Director | Architecture decisions, system integration, build pipeline, canon compliance | Programming Bible — Sections 1, 2 |
| Core Systems Developer | GameManager, PlayerMovement, PerceptionSystem, NotebookSystem, GlitchSystem | Programming Bible — Section 3 |
| AI / Companion Developer | LumiCompanion, NelaCompanion, TrioSystem, dialogue integration | Programming Bible — Section 4 |
| UI Developer | NotebookUI, HUDController, UIManager, all widget systems | Programming Bible — Section 5 |
| Data / Save Developer | SaveSystem, JSON schemas, ScriptableObjects, WorldManager | Programming Bible — Section 6 |

## 2.3 Shared Responsibilities

These responsibilities are shared between both departments and require active coordination:

| Shared Area | Graphic Responsibility | Programming Responsibility |
| --- | --- | --- |
| Anomaly System | Visual design of all anomaly states (7 states per symbol) | C# logic for anomaly triggers, state transitions, echo spawning |
| Notebook System | UI artwork, page designs, ink colour system, animation frames | NotebookSystem.cs, NotebookUI.cs, data persistence |
| Trio Activation | Visual sequence design (gold pulse, symbol formation, hidden layer reveal) | TrioSystem.cs, timing logic, reward distribution |
| Environment States | Art for Normal / Glitch / Activation states of each space | EnvironmentDNA.cs, LightingManager.cs, state machine |
| QA / Canon Check | Visual DNA compliance review against Graphic Bible | System behaviour compliance review against Programming Bible |

# 3. Phase 1 — Pre-Production

PRE-PRODUCTION    |  Months 1–2  |  Weeks 1–8

Pre-Production establishes the complete foundation for both departments. No production asset or script should be created before Pre-Production is complete. The output of this phase is a fully designed, fully planned production system — not a finished product.

Pre-Production Rule: "Plan everything. Build nothing permanent. Validate everything against the Bible."

## 3.1 Graphic Department — Pre-Production Tasks

### Month 1 — Foundation & Style Validation

| Week | Task | Priority | Output | Bible Ref |
| --- | --- | --- | --- | --- |
| W1 | Read and internalise Graphic Production Bible (all 9 sections) | CRITICAL | Team sign-off document | Graphic Bible — All |
| W1 | Establish colour palette master file (World Colour DNA) | CRITICAL | Colour swatch file (.ase) | Graphic Bible — 6.2 |
| W1 | Set up asset folder structure (ABTW_Assets/ hierarchy) | HIGH | Empty folder structure | Graphic Bible — 8.2 |
| W2 | Create character reference sheets — Astra (canonical) | CRITICAL | Astra reference sheet (A3) | Graphic Bible — 3.1 |
| W2 | Create character reference sheets — Lumi (canonical) | CRITICAL | Lumi reference sheet (A3) | Graphic Bible — 3.1 |
| W2 | Create character reference sheets — Nela (canonical) | CRITICAL | Nela reference sheet (A3) | Graphic Bible — 3.1 |
| W3 | Create environment mood boards — East Corridor (3 states) | HIGH | Mood board set | Graphic Bible — 4.3 |
| W3 | Create environment mood boards — Observatory | HIGH | Mood board set | Graphic Bible — 4.4 |
| W3 | Create environment mood boards — Archive / Library | MEDIUM | Mood board set | Graphic Bible — 4.5 |
| W4 | Design anomaly visual language guide (7 states) | CRITICAL | Anomaly style guide | Graphic Bible — 5.4 |
| W4 | Design Notebook UI wireframes (all tabs and states) | HIGH | UI wireframe document | Graphic Bible — 5.3 |
| W4 | Lighting reference guide (warm/cool/mixed profiles) | HIGH | Lighting reference sheet | Graphic Bible — 6.3 |

### Month 2 — Asset Planning & Prototype Art

| Week | Task | Priority | Output | Bible Ref |
| --- | --- | --- | --- | --- |
| W5 | Complete full asset list for Chapter 1 (East Corridor) | CRITICAL | Asset list spreadsheet | Graphic Bible — 8.3 |
| W5 | Create illustration brief template (standard format) | HIGH | Brief template document | Graphic Bible — 7.6 |
| W6 | Prototype: Astra idle pose (concept, not final model) | HIGH | Concept sketch | Graphic Bible — 3.1 |
| W6 | Prototype: East Corridor — Normal state (concept) | HIGH | Environment concept | Graphic Bible — 4.3 |
| W7 | Prototype: Shadow Delay anomaly visual (concept) | HIGH | Anomaly concept | Graphic Bible — 5.4 |
| W7 | Prototype: Notebook UI — first pass (static mockup) | HIGH | UI mockup | Graphic Bible — 5.3 |
| W8 | QA checklist creation (per-illustration checklist) | HIGH | QA checklist document | Graphic Bible — 7.4 |
| W8 | Pre-Production review — all concepts vs. Bible | CRITICAL | Review sign-off | Graphic Bible — 7.5 |

★ MILESTONE: Graphic Pre-Production Complete  —  End of Month 2  [GRAPHIC]

⚡ DEP: Programming must confirm Unity project structure before Graphic begins exporting assets in Alpha.

## 3.2 Programming Department — Pre-Production Tasks

### Month 1 — Architecture & Project Setup

| Week | Task | Priority | Output | Bible Ref |
| --- | --- | --- | --- | --- |
| W1 | Read and internalise Programming Bible (all sections) | CRITICAL | Team sign-off document | Programming Bible — All |
| W1 | Create Unity project (ABTW_Project) with correct folder structure | CRITICAL | Unity project skeleton | Programming Bible — 2.1 |
| W1 | Set up Git repository with .gitignore and branch strategy | HIGH | GitHub repo (ABTW_The_Hidden_System) | Programming Bible — 2.2 |
| W2 | Create GameManager.cs — core system orchestrator | CRITICAL | GameManager.cs (skeleton) | Programming Bible — 3.1 |
| W2 | Create PlayerStats.cs — Awareness, Clarity, Connection, Timing, Stability | CRITICAL | PlayerStats.cs | Programming Bible — 4.1 |
| W2 | Create symbol_map.json — complete symbol catalogue | HIGH | symbol_map.json | Programming Bible — 6.2 |
| W3 | Create PerceptionSystem.cs — core detection logic | CRITICAL | PerceptionSystem.cs | Programming Bible — 3.2 |
| W3 | Create GlitchSystem.cs — anomaly trigger and state machine | CRITICAL | GlitchSystem.cs | Programming Bible — 3.3 |
| W3 | Create AnomalyBase.cs — base class for all anomalies | HIGH | AnomalyBase.cs | Programming Bible — 3.4 |
| W4 | Create NotebookSystem.cs — Record/Wait logic | CRITICAL | NotebookSystem.cs | Programming Bible — 3.5 |
| W4 | Create EchoSystem.cs — echo spawning and management | HIGH | EchoSystem.cs | Programming Bible — 3.6 |
| W4 | Create WorldManager.cs — world state tracking | HIGH | WorldManager.cs | Programming Bible — 3.7 |

### Month 2 — System Integration & Prototype Level

| Week | Task | Priority | Output | Bible Ref |
| --- | --- | --- | --- | --- |
| W5 | Create PlayerMovement.cs — 3rd person movement | CRITICAL | PlayerMovement.cs | Programming Bible — 3.1 |
| W5 | Create CameraController.cs — cinematic follow camera | HIGH | CameraController.cs | Programming Bible — 3.1 |
| W6 | Create ShadowDelayAnomaly.cs — Chapter 1 primary anomaly | CRITICAL | ShadowDelayAnomaly.cs | Programming Bible — 3.4 |
| W6 | Create TrioSystem.cs — synchronisation logic | HIGH | TrioSystem.cs | Programming Bible — 3.8 |
| W7 | Build prototype EastCorridor.unity scene (grey-box) | CRITICAL | EastCorridor.unity (grey-box) | Programming Bible — 5.1 |
| W7 | Integrate GameManager with all core systems (wire-up) | CRITICAL | Integrated build (no crash) | Programming Bible — 3.1 |
| W8 | First playable build — movement + 1 glitch + notebook open | CRITICAL | Prototype EXE | Programming Bible — 5.2 |
| W8 | Pre-Production review — all systems vs. Bible | CRITICAL | Review sign-off | Programming Bible — All |

★ MILESTONE: Programming Pre-Production Complete  —  End of Month 2  [PROGRAMMING]

★ MILESTONE: JOINT MILESTONE: Prototype Build Approved  —  End of Month 2  [BOTH DEPARTMENTS]

⚡ DEP: Graphic department must deliver character reference sheets before Programming creates Player_Astra.prefab.

# 4. Phase 2 — Alpha

ALPHA    |  Months 3–6  |  Weeks 9–24

Alpha is the core production phase. Both departments work in parallel to build the primary systems and assets for Chapter 1 (East Corridor). The Alpha milestone is a fully playable Chapter 1 — functional, not polished. All core mechanics must work. All primary assets must be in-engine.

Alpha Rule: "Functional over beautiful. Every system must work. Every asset must be in-engine. Polish comes in Beta."

## 4.1 Graphic Department — Alpha Tasks

### Month 3 — Character Production

| Week | Task | Priority | Output | Bible Ref |
| --- | --- | --- | --- | --- |
| W9 | Astra — final 3D model (low-poly, stylized) | CRITICAL | Astra.fbx | Graphic Bible — 3.1 |
| W9 | Astra — texture set (diffuse, normal, emission) | CRITICAL | Astra_textures/ | Graphic Bible — 6.4 |
| W10 | Astra — expression sheet (idle, notice, wait, record) | HIGH | Astra_expressions.png | Graphic Bible — 3.1 |
| W10 | Lumi — final 3D model + texture set | HIGH | Lumi.fbx + textures | Graphic Bible — 3.1 |
| W11 | Nela — final 3D model + texture set | HIGH | Nela.fbx + textures | Graphic Bible — 3.1 |
| W11 | Nimbus — concept + 3D model (luminous companion entity) | MEDIUM | Nimbus.fbx | Graphic Bible — 3.2 |
| W12 | Character QA — all three vs. canonical reference sheets | CRITICAL | QA sign-off | Graphic Bible — 3.3 |

### Month 4 — Environment Production (East Corridor)

| Week | Task | Priority | Output | Bible Ref |
| --- | --- | --- | --- | --- |
| W13 | East Corridor — Normal state (full 3D environment) | CRITICAL | EastCorridor_Normal.fbx | Graphic Bible — 4.3 |
| W13 | East Corridor — texture set (stone, wood, glass) | CRITICAL | EastCorridor_textures/ | Graphic Bible — 6.4 |
| W14 | East Corridor — Glitch state visual variants | CRITICAL | EastCorridor_Glitch assets | Graphic Bible — 4.3 |
| W14 | East Corridor — Activation state visual variants | HIGH | EastCorridor_Activation assets | Graphic Bible — 4.3 |
| W15 | Lighting profiles — Morning, Afternoon, Sunset, Night, Rain | HIGH | LightingProfile.asset (×5) | Graphic Bible — 6.3 |
| W15 | Shadow Delay anomaly — all 7 visual states | CRITICAL | ShadowDelay_states/ (×7) | Graphic Bible — 5.4 |
| W16 | Environment QA — East Corridor vs. Bible specifications | CRITICAL | QA sign-off | Graphic Bible — 7.4 |

### Month 5 — UI Production

| Week | Task | Priority | Output | Bible Ref |
| --- | --- | --- | --- | --- |
| W17 | Notebook UI — cover design (leather, navy-indigo) | CRITICAL | Notebook_cover.png | Graphic Bible — 5.3 |
| W17 | Notebook UI — page designs (ivory, cream texture) | CRITICAL | Notebook_pages.png | Graphic Bible — 5.3 |
| W18 | Notebook UI — tab system (Patterns, Symbols, Connections, Memory) | HIGH | Notebook_tabs.png | Graphic Bible — 5.3 |
| W18 | Notebook UI — RECORD and WAIT button designs | CRITICAL | Notebook_buttons.png | Graphic Bible — 5.3 |
| W19 | HUD — Perception Ring design (awareness indicator) | HIGH | HUD_PerceptionRing.png | Graphic Bible — 5.1 |
| W19 | HUD — stat indicators (Awareness, Clarity, Connection) | HIGH | HUD_stats.png | Graphic Bible — 5.1 |
| W20 | UI QA — all UI elements vs. Bible specifications | HIGH | QA sign-off | Graphic Bible — 7.4 |

### Month 6 — FX & Integration Support

| Week | Task | Priority | Output | Bible Ref |
| --- | --- | --- | --- | --- |
| W21 | Soft light shader — painterly, no specular highlights | CRITICAL | SoftShader.shader | Graphic Bible — 6.4 |
| W21 | Perception shader — subtle desaturation effect | HIGH | PerceptionShader.shader | Graphic Bible — 6.4 |
| W22 | Trio Activation FX — gold pulse (subtle, not explosive) | CRITICAL | TrioActivation_FX.prefab | Graphic Bible — 5.7 |
| W22 | Symbol formation FX — 7-state visual sequence | HIGH | Symbol_FX/ (×7) | Graphic Bible — 5.5 |
| W23 | Echo anomaly visual — faded, 40% intensity version | HIGH | Echo_FX.prefab | Graphic Bible — 5.6 |
| W23 | Memory Walk visual — blur, desaturation, slow-motion overlay | MEDIUM | MemoryWalk_FX.prefab | Graphic Bible — 5.8 |
| W24 | Alpha integration support — assist Programming with asset import | HIGH | All assets in-engine | Graphic Bible — 8.2 |

★ MILESTONE: Graphic Alpha Complete — All Chapter 1 Assets In-Engine  —  End of Month 6  [GRAPHIC]

⚡ DEP: All character models, environment assets, UI artwork, and FX must be imported and functional in Unity before Beta begins.

## 4.2 Programming Department — Alpha Tasks

### Month 3 — Core Systems Completion

| Week | Task | Priority | Output | Bible Ref |
| --- | --- | --- | --- | --- |
| W9 | Complete PerceptionSystem.cs — 2-second observation timer | CRITICAL | PerceptionSystem.cs (final) | Programming Bible — 3.2 |
| W9 | Complete GlitchSystem.cs — trigger, evolve, remove logic | CRITICAL | GlitchSystem.cs (final) | Programming Bible — 3.3 |
| W10 | Complete ShadowDelayAnomaly.cs — 0.3–0.5s delay shader | CRITICAL | ShadowDelayAnomaly.cs | Programming Bible — 3.4 |
| W10 | Complete NotebookSystem.cs — Record/Wait/Deep Record | CRITICAL | NotebookSystem.cs (final) | Programming Bible — 3.5 |
| W11 | Complete EchoSystem.cs — echo spawning at 40% intensity | HIGH | EchoSystem.cs (final) | Programming Bible — 3.6 |
| W11 | Complete TrioSystem.cs — 3-second wait trigger | HIGH | TrioSystem.cs (final) | Programming Bible — 3.8 |
| W12 | Complete WorldManager.cs — state tracking (time, season, symbol) | HIGH | WorldManager.cs (final) | Programming Bible — 3.7 |

### Month 4 — Companion & Quest Systems

| Week | Task | Priority | Output | Bible Ref |
| --- | --- | --- | --- | --- |
| W13 | LumiCompanion.cs — analysis AI, notebook auto-draw trigger | HIGH | LumiCompanion.cs | Programming Bible — 4.1 |
| W13 | NelaCompanion.cs — timing AI, "wait… now" trigger | HIGH | NelaCompanion.cs | Programming Bible — 4.2 |
| W14 | DialogueSystem.cs — character dialogue and subtitles | HIGH | DialogueSystem.cs | Programming Bible — 4.3 |
| W14 | AnomalySpawner.cs — spawn table and timing logic | HIGH | AnomalySpawner.cs | Programming Bible — 3.9 |
| W15 | Quest system — "The Repeating Shadow" (Chapter 1 primary quest) | CRITICAL | Quest_RepeatingShallow.cs | Programming Bible — 5.3 |
| W15 | MemoryWalkSystem.cs — time slow, visual change, no input | MEDIUM | MemoryWalkSystem.cs | Programming Bible — 3.10 |
| W16 | SaveSystem.cs — JSON save/load for world state | HIGH | SaveSystem.cs + SaveData.json | Programming Bible — 6.1 |

### Month 5 — UI Systems

| Week | Task | Priority | Output | Bible Ref |
| --- | --- | --- | --- | --- |
| W17 | NotebookUI.cs — full UI controller (tabs, entries, buttons) | CRITICAL | NotebookUI.cs | Programming Bible — 5.1 |
| W17 | UI_Notebook.prefab — complete notebook widget | CRITICAL | UI_Notebook.prefab | Programming Bible — 5.1 |
| W18 | HUDController.cs — perception ring, stat display | HIGH | HUDController.cs | Programming Bible — 5.2 |
| W18 | UIManager.cs — show/hide all UI elements | HIGH | UIManager.cs | Programming Bible — 5.2 |
| W19 | Pattern entry system — dynamic notebook entries | HIGH | PatternEntry.cs | Programming Bible — 5.1 |
| W19 | Echo entry system — faded notebook entries | HIGH | EchoEntry.cs | Programming Bible — 5.1 |
| W20 | UI integration test — all UI with all systems | CRITICAL | Integration test report | Programming Bible — 5.4 |

### Month 6 — Level Build & Alpha Integration

| Week | Task | Priority | Output | Bible Ref |
| --- | --- | --- | --- | --- |
| W21 | EastCorridor.unity — full level build (replace grey-box) | CRITICAL | EastCorridor.unity (final Alpha) | Programming Bible — 5.1 |
| W21 | Lighting integration — all 5 time-of-day profiles | HIGH | LightingManager.cs integrated | Programming Bible — 5.1 |
| W22 | Shader integration — SoftShader + PerceptionShader | HIGH | Shaders in-engine | Programming Bible — 5.5 |
| W22 | FX integration — Trio Activation, Symbol Formation, Echo | HIGH | All FX in-engine | Programming Bible — 5.5 |
| W23 | Full system integration test — all systems in one scene | CRITICAL | Integration test (pass/fail) | Programming Bible — 7.1 |
| W23 | Alpha build — playable EXE (Chapter 1, East Corridor) | CRITICAL | ABTW_Alpha_v1.exe | Programming Bible — 7.2 |
| W24 | Alpha review — both departments, canon compliance check | CRITICAL | Alpha review sign-off | Programming Bible — 7.3 |

★ MILESTONE: Programming Alpha Complete — Playable Chapter 1 Build  —  End of Month 6  [PROGRAMMING]

★ MILESTONE: JOINT MILESTONE: Alpha Build Approved  —  End of Month 6  [BOTH DEPARTMENTS]

⚡ DEP: Alpha approval requires: all core systems functional, all Chapter 1 assets in-engine, no critical bugs, canon compliance confirmed.

# 5. Phase 3 — Beta

BETA    |  Months 7–10  |  Weeks 25–40

Beta is the full content phase. Both departments expand from Chapter 1 to the complete game scope (Chapters 1–4, Arc 1 — Discovery). All assets are completed, all systems are integrated, and the full game is QA-ready by the end of Beta.

Beta Rule: "Complete everything. Polish everything. Test everything. The world must feel alive, not assembled."

## 5.1 Graphic Department — Beta Tasks

### Month 7 — Remaining Environments

| Week | Task | Priority | Output | Bible Ref |
| --- | --- | --- | --- | --- |
| W25 | Observatory — full 3D environment (all states) | HIGH | Observatory.fbx + states | Graphic Bible — 4.4 |
| W26 | Archive / Library — full 3D environment (3 levels) | HIGH | Archive.fbx + states | Graphic Bible — 4.5 |
| W27 | Classrooms — full 3D environment | MEDIUM | Classroom.fbx | Graphic Bible — 4.2 |
| W28 | Dormitories — Astra room + common areas | MEDIUM | Dormitory.fbx | Graphic Bible — 4.2 |

### Month 8 — Supporting Characters & Seasonal Assets

| Week | Task | Priority | Output | Bible Ref |
| --- | --- | --- | --- | --- |
| W29 | Prof. Lyra Quill — 3D model + texture set | HIGH | ProfQuill.fbx + textures | Graphic Bible — 3.2 |
| W30 | Archivist Noctra — 3D model + texture set | HIGH | Noctra.fbx + textures | Graphic Bible — 3.2 |
| W31 | Orion Vex — 3D model + texture set | MEDIUM | OrionVex.fbx + textures | Graphic Bible — 3.2 |
| W31 | Mr. Vale / The Curator — 3D model + texture set | MEDIUM | MrVale.fbx + textures | Graphic Bible — 3.2 |
| W32 | Seasonal variants — all environments × 4 seasons | HIGH | Seasonal asset sets (×4) | Graphic Bible — 4.6 |

### Month 9 — Symbol System & Remaining Anomalies

| Week | Task | Priority | Output | Bible Ref |
| --- | --- | --- | --- | --- |
| W33 | All 8 symbols — complete visual design (7 states each) | CRITICAL | Symbol_[ID]/ (×8 × 7 states) | Graphic Bible — 5.5 |
| W34 | Reflected Word anomaly — all visual states | HIGH | ReflectedWord_states/ | Graphic Bible — 5.4 |
| W35 | Echo Corridor anomaly — all visual states | HIGH | EchoCorridor_states/ | Graphic Bible — 5.4 |
| W35 | Memory Trace anomaly — all visual states | HIGH | MemoryTrace_states/ | Graphic Bible — 5.4 |
| W36 | Garden Spiral anomaly — all visual states | MEDIUM | GardenSpiral_states/ | Graphic Bible — 5.4 |

### Month 10 — Polish, Promotional & QA

| Week | Task | Priority | Output | Bible Ref |
| --- | --- | --- | --- | --- |
| W37 | Full visual polish pass — all environments | HIGH | Polished environment set | Graphic Bible — 7.1 |
| W38 | Promotional materials — key art, cover illustration | HIGH | Key art (A2, 300 DPI) | Graphic Bible — 7.3 |
| W39 | Full QA pass — all assets vs. Graphic Bible (8-point checklist) | CRITICAL | QA report (all pass) | Graphic Bible — 7.4 |
| W40 | Beta review — all assets approved for Gold | CRITICAL | Beta sign-off | Graphic Bible — 7.5 |

★ MILESTONE: Graphic Beta Complete — All Assets QA-Approved  —  End of Month 10  [GRAPHIC]

⚡ DEP: All Beta assets must be imported and tested in the Beta build before Gold phase begins.

## 5.2 Programming Department — Beta Tasks

### Month 7 — Remaining Anomaly Scripts

| Week | Task | Priority | Output | Bible Ref |
| --- | --- | --- | --- | --- |
| W25 | ReflectionMismatchAnomaly.cs — reflected word system | HIGH | ReflectionMismatchAnomaly.cs | Programming Bible — 3.4 |
| W26 | SoundEchoAnomaly.cs — footstep echo delay system | HIGH | SoundEchoAnomaly.cs | Programming Bible — 3.4 |
| W27 | LightInstabilityAnomaly.cs — light flicker system | HIGH | LightInstabilityAnomaly.cs | Programming Bible — 3.4 |
| W28 | SymbolFragmentAnomaly.cs — symbol formation system | HIGH | SymbolFragmentAnomaly.cs | Programming Bible — 3.4 |

### Month 8 — Remaining Levels & World Systems

| Week | Task | Priority | Output | Bible Ref |
| --- | --- | --- | --- | --- |
| W29 | Observatory.unity — full level build | HIGH | Observatory.unity | Programming Bible — 5.1 |
| W30 | Archive.unity — full level build (3 levels) | HIGH | Archive.unity | Programming Bible — 5.1 |
| W31 | Classroom.unity + Dormitory.unity — full level builds | MEDIUM | Classroom.unity, Dormitory.unity | Programming Bible — 5.1 |
| W31 | TimeSystem — day/night cycle affecting anomaly frequency | HIGH | TimeSystem.cs | Programming Bible — 3.7 |
| W32 | WeatherSystem — rain/fog affecting perception stats | HIGH | WeatherSystem.cs | Programming Bible — 3.7 |

### Month 9 — Academy Rank & Full Quest System

| Week | Task | Priority | Output | Bible Ref |
| --- | --- | --- | --- | --- |
| W33 | Academy Rank system — 10 ranks, unlock logic | HIGH | AcademyRank.cs | Programming Bible — 4.4 |
| W34 | Full quest system — all Chapter 1–4 quests | HIGH | Quest scripts (×12) | Programming Bible — 5.3 |
| W35 | Chapter select system — chapter progression tracking | HIGH | ChapterManager.cs | Programming Bible — 5.4 |
| W36 | Full save/load system — all world state variables | HIGH | SaveSystem.cs (complete) | Programming Bible — 6.1 |

### Month 10 — Integration, QA & Beta Build

| Week | Task | Priority | Output | Bible Ref |
| --- | --- | --- | --- | --- |
| W37 | Full system integration — all scripts, all levels, all assets | CRITICAL | Integrated Beta build | Programming Bible — 7.1 |
| W38 | Performance optimisation — target 60fps on minimum spec | HIGH | Performance report | Programming Bible — 7.4 |
| W39 | Full QA pass — all systems vs. Programming Bible | CRITICAL | QA report (all pass) | Programming Bible — 7.3 |
| W40 | Beta build — full game EXE (all chapters) | CRITICAL | ABTW_Beta_v1.exe | Programming Bible — 7.2 |

★ MILESTONE: Programming Beta Complete — Full Game Build QA-Ready  —  End of Month 10  [PROGRAMMING]

★ MILESTONE: JOINT MILESTONE: Beta Build Approved  —  End of Month 10  [BOTH DEPARTMENTS]

⚡ DEP: Beta approval requires: all systems functional, all assets in-engine, full QA pass, no critical bugs, performance targets met.

# 6. Phase 4 — Gold / Launch

GOLD / LAUNCH    |  Months 11–12  |  Weeks 41–48

Gold is the final phase. Both departments focus on polish, certification, and release preparation. No new features or assets are added in Gold — only fixes, polish, and launch preparation. The Gold milestone is the final, canon-locked, release-ready build.

Gold Rule: "No new features. No new assets. Only polish, fix, and release. The world is complete."

## 6.1 Graphic Department — Gold Tasks

| Week | Task | Priority | Output | Bible Ref |
| --- | --- | --- | --- | --- |
| W41 | Final visual polish — all environments (lighting, colour grading) | HIGH | Final environment set | Graphic Bible — 7.1 |
| W42 | Final character polish — all models, textures, expressions | HIGH | Final character set | Graphic Bible — 3.3 |
| W43 | Store assets — Steam capsule art, screenshots, trailer frames | HIGH | Store asset package | Graphic Bible — 7.3 |
| W44 | Final UI polish — all screens, all states, all animations | HIGH | Final UI set | Graphic Bible — 7.4 |
| W45 | Final QA — complete visual DNA check (all assets) | CRITICAL | Final QA report (all pass) | Graphic Bible — 7.4 |
| W46 | Gold sign-off — Art Director approval on all assets | CRITICAL | Gold art sign-off | Graphic Bible — 7.5 |
| W47–48 | Launch support — hotfix assets if required | HIGH | Hotfix asset package (if needed) | Graphic Bible — All |

★ MILESTONE: Graphic Gold Complete — All Assets Canon-Locked  —  End of Month 11  [GRAPHIC]

## 6.2 Programming Department — Gold Tasks

| Week | Task | Priority | Output | Bible Ref |
| --- | --- | --- | --- | --- |
| W41 | Final bug fix pass — all critical and high-priority bugs | CRITICAL | Bug fix report | Programming Bible — 7.3 |
| W42 | Final performance pass — all levels at 60fps target | HIGH | Performance report (final) | Programming Bible — 7.4 |
| W43 | Build pipeline — final EXE, installer, Steam integration | CRITICAL | ABTW_Gold_v1.exe + installer | Programming Bible — 7.5 |
| W44 | Save system final test — all save/load scenarios | HIGH | Save system test report | Programming Bible — 6.1 |
| W45 | Final QA — complete system compliance check | CRITICAL | Final QA report (all pass) | Programming Bible — 7.3 |
| W46 | Gold build — final release EXE | CRITICAL | ABTW_Gold_FINAL.exe | Programming Bible — 7.5 |
| W47–48 | Launch support — hotfix patches if required | HIGH | Hotfix build (if needed) | Programming Bible — All |

★ MILESTONE: Programming Gold Complete — Final Build Released  —  End of Month 12  [PROGRAMMING]

★ MILESTONE: JOINT MILESTONE: GOLD — ABTW: THE HIDDEN SYSTEM RELEASED  —  End of Month 12  [BOTH DEPARTMENTS]

# 7. Inter-Department Dependencies

These dependencies are hard requirements. The receiving department cannot proceed until the delivering department has completed the listed deliverable. Missing a dependency triggers a mandatory cross-department review.

| ID | Delivering Dept | Deliverable | Receiving Dept | Required By | Phase |
| --- | --- | --- | --- | --- | --- |
| DEP-01 | GRAPHIC | Astra canonical reference sheet | PROGRAMMING | Player_Astra.prefab creation | Pre-Production |
| DEP-02 | GRAPHIC | Lumi + Nela reference sheets | PROGRAMMING | Companion prefab creation | Pre-Production |
| DEP-03 | PROGRAMMING | Unity project folder structure confirmed | GRAPHIC | Asset export format decisions | Pre-Production |
| DEP-04 | PROGRAMMING | AnomalyBase.cs API defined | GRAPHIC | Anomaly visual state count confirmed | Pre-Production |
| DEP-05 | GRAPHIC | Colour palette master file (.ase) | PROGRAMMING | Shader colour values | Pre-Production |
| DEP-06 | GRAPHIC | Astra.fbx + textures (final) | PROGRAMMING | Player_Astra.prefab (final) | Alpha Month 3 |
| DEP-07 | GRAPHIC | EastCorridor_Normal.fbx + textures | PROGRAMMING | EastCorridor.unity level build | Alpha Month 4 |
| DEP-08 | GRAPHIC | ShadowDelay_states/ (×7) | PROGRAMMING | ShadowDelayAnomaly.cs visual integration | Alpha Month 4 |
| DEP-09 | GRAPHIC | Notebook UI artwork (all states) | PROGRAMMING | NotebookUI.cs + UI_Notebook.prefab | Alpha Month 5 |
| DEP-10 | GRAPHIC | SoftShader.shader + PerceptionShader.shader | PROGRAMMING | Shader integration in-engine | Alpha Month 6 |
| DEP-11 | GRAPHIC | TrioActivation_FX.prefab | PROGRAMMING | TrioSystem.cs visual trigger | Alpha Month 6 |
| DEP-12 | PROGRAMMING | Alpha build approved (EXE) | GRAPHIC | Beta asset production begins | Alpha End |
| DEP-13 | GRAPHIC | All 8 symbols (7 states each) | PROGRAMMING | SymbolFragmentAnomaly.cs integration | Beta Month 9 |
| DEP-14 | GRAPHIC | All supporting character models | PROGRAMMING | NPC prefab creation | Beta Month 8 |
| DEP-15 | PROGRAMMING | Beta build approved (EXE) | GRAPHIC | Gold polish pass begins | Beta End |
| DEP-16 | GRAPHIC | Gold art sign-off | PROGRAMMING | Gold build compilation | Gold Month 11 |

# 8. Task Priority Matrix

All tasks in this schedule are assigned one of four priority levels. Priority determines the order of work when resources are constrained and the severity of impact if the task is delayed.

| Priority | Definition | Impact if Delayed | Examples |
| --- | --- | --- | --- |
| CRITICAL | Blocks all other work. Must be completed before any dependent task can begin. | Phase milestone missed. Production halts. | GameManager.cs, Astra reference sheet, Alpha build |
| HIGH | Required for phase completion. Can be done in parallel with other HIGH tasks. | Phase milestone at risk. Requires overtime. | All environment assets, companion scripts, UI systems |
| MEDIUM | Required for full game scope. Can be deferred to next phase if necessary. | Scope reduction. Feature may be cut or simplified. | Supporting characters, seasonal variants, Memory Walk |
| LOW | Enhancement or polish. Can be cut without affecting core gameplay. | Reduced polish. No gameplay impact. | Promotional materials, optional FX variants |

## 8.1 Critical Path — Minimum Viable Build

The following tasks form the critical path — the minimum set of tasks required to produce a playable, canon-compliant Chapter 1 build. All other tasks are secondary to this path.

| Step | Task | Dept | Phase |
| --- | --- | --- | --- |
| 1 | Read and sign off on both Production Bibles | BOTH | Pre-Production |
| 2 | Astra canonical reference sheet | GRAPHIC | Pre-Production |
| 3 | Unity project structure + GameManager.cs | PROGRAMMING | Pre-Production |
| 4 | PerceptionSystem.cs + GlitchSystem.cs | PROGRAMMING | Pre-Production |
| 5 | NotebookSystem.cs (Record/Wait) | PROGRAMMING | Pre-Production |
| 6 | Prototype EXE (movement + 1 glitch + notebook) | PROGRAMMING | Pre-Production |
| 7 | Astra.fbx + textures (final) | GRAPHIC | Alpha Month 3 |
| 8 | EastCorridor_Normal.fbx + all states | GRAPHIC | Alpha Month 4 |
| 9 | ShadowDelay_states/ (×7) | GRAPHIC | Alpha Month 4 |
| 10 | Notebook UI artwork (all states) | GRAPHIC | Alpha Month 5 |
| 11 | SoftShader.shader | GRAPHIC | Alpha Month 6 |
| 12 | EastCorridor.unity (full level build) | PROGRAMMING | Alpha Month 6 |
| 13 | Alpha build — playable EXE | PROGRAMMING | Alpha End |

# 9. Milestone Summary

All milestones are hard deadlines. Missing a milestone triggers a mandatory cross-department review before the next phase begins. No phase may begin until all milestones from the previous phase are approved.

| Milestone | Date | Department | Approval Required From |
| --- | --- | --- | --- |
| Graphic Pre-Production Complete | End of Month 2 | GRAPHIC | Art Director |
| Programming Pre-Production Complete | End of Month 2 | PROGRAMMING | Technical Director |
| JOINT: Prototype Build Approved | End of Month 2 | BOTH | Both Directors |
| Graphic Alpha Complete | End of Month 6 | GRAPHIC | Art Director |
| Programming Alpha Complete | End of Month 6 | PROGRAMMING | Technical Director |
| JOINT: Alpha Build Approved | End of Month 6 | BOTH | Both Directors + QA |
| Graphic Beta Complete | End of Month 10 | GRAPHIC | Art Director |
| Programming Beta Complete | End of Month 10 | PROGRAMMING | Technical Director |
| JOINT: Beta Build Approved | End of Month 10 | BOTH | Both Directors + QA |
| Graphic Gold Complete | End of Month 11 | GRAPHIC | Art Director |
| Programming Gold Complete | End of Month 12 | PROGRAMMING | Technical Director |
| JOINT: GOLD — GAME RELEASED | End of Month 12 | BOTH | Full Team + Publisher |

# 10. Canon Compliance Rules

All production work — graphic and programming — must comply with the canonical ABTW world rules at all times. These rules are derived from the ABTW Legendary Master World Bible v1.0 (Full Canon Lock) and are enforced through both Production Bibles.

"The Academy does not reveal itself. It responds to perception." — This principle governs every asset and every script in ABTW production.

## 10.1 Graphic Canon Rules

| Rule | Requirement | Violation = Regenerate |
| --- | --- | --- |
| Character Visual DNA | Characters must match canonical reference sheets exactly. No visual redesigns. | YES — full regeneration required |
| Colour DNA | All colours must be within the approved World Colour DNA palette. | YES — colour correction required |
| Anomaly Subtlety | Anomalies must be subtle. 70% normal, 30% strange. No flashy effects. | YES — redesign required |
| Forbidden Directions | No combat poses, horror elements, cyberpunk drift, or spectacle fantasy. | YES — full regeneration required |
| Scale Rule | Environments must feel larger than characters. Always. | YES — scale correction required |
| Lighting Emotional Function | Lighting must match the emotional function of the space and time of day. | YES — lighting revision required |

## 10.2 Programming Canon Rules

| Rule | Requirement | Violation = Refactor |
| --- | --- | --- |
| Perception Over Power | No combat systems, no damage systems, no power-based progression. | YES — full refactor required |
| Notebook as Reality Tool | The Notebook must affect world state. It is not a UI log. | YES — system refactor required |
| Echo Not Reset | Closed paths create Echoes. The world never resets. | YES — Echo system refactor required |
| Trio Synchronisation | Trio Activation requires all three conditions. No shortcuts. | YES — TrioSystem refactor required |
| Consequence Without Punishment | No "game over" states. Every decision leads to a different reality. | YES — quest system refactor required |
| World State Persistence | All world state changes must be saved and persist across sessions. | YES — SaveSystem refactor required |

## 10.3 Forbidden Production Directions

These directions are explicitly forbidden in all ABTW production. Any work moving in these directions must be stopped and reviewed immediately:

| Forbidden Direction | Graphic Impact | Programming Impact |
| --- | --- | --- |
| Combat / Action | No combat poses, impact frames, weapon designs | No damage systems, no combat scripts, no health bars |
| Horror / Grimdark | No threatening darkness, no body horror, no decay | No jump scare triggers, no threat-based mechanics |
| Spectacle Fantasy | No explosions, no dramatic magical displays, no dragons | No particle explosion FX, no dramatic power systems |
| Cyberpunk / Sci-Fi | No neon lights, no digital interfaces, no futuristic elements | No tech-based UI, no digital aesthetic in code |
| Game-Level Feeling | Environments must feel like real places, not game levels | No visible level boundaries, no checkpoint markers |
| Empty Architecture | Every space must feel inhabited and emotionally alive | Social life systems must populate all spaces |

ACADEMY BEYOND THIS WORLD: THE HIDDEN SYSTEM

Master Production Schedule — Version 1.0 — Full Production Authority

This document governs all production activity for both the Graphic and Programming departments.